## Dashboard
AYUR CENTRE PTE. LTD. — Clinic Management System
Project Tracker — Last Updated: 31 March 2026
PROJECT SUMMARY
Total Modules | 12 |  | Total Pages | 60 |  | Total API Endpoints | 108
Database Models | 41 |  | Days Since Kickoff |  |  | Commits | 44
MODULE STATUS OVERVIEW
Module | Pages | API Endpoints | Status | Completion % | Tester | Priority | Notes
Patient Management | 3 | 8 | Live | 95% |  | P0 | NRIC validation, duplicate detection done
Appointments | 2 | 4 | Live | 90% |  | P0 | Calendar view, slot management
Billing & Invoicing | 4 | 10 | Live | 90% |  | P0 | Invoices, payments, credit notes
Inventory Management | 15 | 32 | Live | 95% |  | P0 | Full stock lifecycle, transfers, PO, 45+ sub-features
Doctor Portal | 2 | 3 | Live | 85% |  | P1 | Dashboard, prescriptions, clinical notes
Treatment Plans | 5 | 8 | Live | 85% |  | P1 | Plans, milestones, progress tracking
Packages | 3 | 8 | Live | 85% |  | P1 | Package purchase, sessions, sharing, refunds
Communications | 4 | 10 | Live | 80% |  | P2 | Email, WhatsApp, SMS, templates, bulk
Insurance | 2 | 4 | Live | 75% |  | P2 | Providers, claims
Reports | 1 | 5 | Live | 80% |  | P1 | Revenue, inventory, insurance, transfers
Admin & Security | 6 | 14 | Live | 90% |  | P0 | Auth, 2FA, roles, audit log, branches
Multi-Branch | 3 | 6 | Live | 90% |  | P0 | Branch stock, transfers, comparison

## Feature Tracker
Feature ID | Module | Feature Name | What Was Requested | What Was Delivered | Status | Date Completed | Commit Hash | Priority | Tester | Test Status | Bugs Found | Marketing Tag | Notes
F001 | Patients | Patient Registration Form | Create patient registration form | Full registration with 30+ fields, label:input layout, SG address format | Completed | 2026-03-31 | 2a30cc8 | P0 |  | Pending |  | Patient Onboarding
F002 | Patients | Form Redesign — Label:Input Layout | Redesign form to label-on-left, input-on-right vertical layout | Flex-based layout with w-40 labels, consistent spacing across all sections | Completed | 2026-03-31 | 3a627ea | P0 |  | Pending |  |  | User showed reference screenshot
F003 | Patients | Uniform Field Width (350px) | Make all fields uniform width, not too long | fieldMaxWidth=350px constant applied to all input fields globally | Completed | 2026-03-31 | 3a627ea | P0 |  | Pending
F004 | Patients | NRIC Checksum Validation | Validate Singapore NRIC structure (9 chars, S/T/F/G/M prefix, checksum) | Full checksum algorithm, auto-uppercase, real-time validation on blur/change, server-side validation | Completed | 2026-03-31 | 7ca6dcd | P0 |  | Pending |  | Singapore Compliance | Supports S/T (citizens), F/G/M (foreigners)
F005 | Patients | Duplicate Detection — NRIC | Prevent duplicate NRIC registrations | Real-time check on blur, hard-block with 'Open Existing Profile' button | Completed | 2026-03-31 | 3a627ea | P0 |  | Pending |  | Data Integrity | Hard block — cannot proceed with duplicate NRIC
F006 | Patients | Duplicate Detection — Phone | Prevent duplicate phone registrations | Real-time check with suffix matching, soft warning with override option | Completed | 2026-03-31 | 3a627ea | P0 |  | Pending |  | Data Integrity | Soft block — can override with 'Different person, continue'
F007 | Patients | Duplicate Detection — Email | Prevent duplicate email registrations | Real-time check, case-insensitive, soft warning | Completed | 2026-03-31 | 3a627ea | P1 |  | Pending
F008 | Patients | Phone Normalization on Save | Normalize phone numbers for consistent storage | Auto-adds +65 for SG (8-digit), +91 for IN (10-digit), strips formatting | Completed | 2026-03-31 | 7ca6dcd | P0 |  | Pending |  | Multi-Country | Applied to all phone fields: primary, secondary, whatsapp, emergency
F009 | Patients | Cross-Field Phone Validation | Secondary mobile ≠ primary, emergency ≠ own phone | Frontend + API validation on both POST and PUT routes | Completed | 2026-03-31 | 7ca6dcd | P1 |  | Pending
F010 | Patients | Email Lowercase Normalization | Store emails in consistent format | Auto-lowercase on save in both POST and PUT routes | Completed | 2026-03-31 | 7ca6dcd | P1 |  | Pending
F011 | Patients | Patient Detail View | View full patient profile | Comprehensive profile with tabs for appointments, notes, documents, vitals | Completed | 2026-03-28 | 3fd92f7 | P0 |  | Pending
F012 | Patients | Patient Photo Upload | Upload patient photo | Photo upload API with file storage | Completed | 2026-03-28 | 3fd92f7 | P2 |  | Pending
F013 | Patients | Family Members Linking | Link family members to patients | Relation dropdown, search existing patients, gender-aware labels | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F014 | Patients | Patient Timeline | View patient activity history | Timeline API showing appointments, notes, communications chronologically | Completed | 2026-03-28 | 3fd92f7 | P2 |  | Pending
F020 | Inventory | Inventory List Page | Main inventory listing with search/filter | Paginated list with search, category filter, stock status badges, A-Z sorting | Completed | 2026-03-30 | f572d67 | P0 |  | Pending |  | Stock Management | 15 pages, 12 inventory pages
F021 | Inventory | Inventory Item Detail Page | Detailed view of single inventory item | Sub-tabs: Overview, Transactions, Movement Graph, Stock by Branch | Completed | 2026-03-30 | 2c84221 | P0 |  | Pending |  |  | Enriched transaction history
F022 | Inventory | Add New Inventory Item | Form to create inventory items | Full form with name, category, unit, reorder point, supplier, variants | Completed | 2026-03-30 | f572d67 | P0 |  | Pending
F023 | Inventory | Edit Inventory Item | Update existing inventory item details | Edit form with all fields, variant management | Completed | 2026-03-30 | f572d67 | P0 |  | Pending
F024 | Inventory | Inventory Variants | Support product variants (sizes, concentrations) | InventoryVariant model with per-variant pricing, variant picker in billing | Completed | 2026-03-30 | f572d67 | P0 |  | Pending |  |  | Billing shows variant dropdown
F025 | Inventory | Inventory Overhaul — Units & Categories | Correct units of measure, proper categorization | Ayurvedic-specific units (ml, g, tablets, sachets), proper categories | Completed | 2026-03-30 | f572d67 | P0 |  | Pending |  |  | Initial data was using wrong units
F026 | Inventory | Transaction History | Track all stock transactions per item | StockTransaction model: purchase, sale, adjustment, transfer, write-off | Completed | 2026-03-30 | 2c84221 | P1 |  | Pending |  | Audit Trail | API: /api/inventory/[id]/transactions
F027 | Inventory | Stock Movement API | API endpoint for stock movements | Records stock in/out with reason, batch, reference | Completed | 2026-03-30 | 2c84221 | P1 |  | Pending |  |  | API: /api/inventory/[id]/movement
F028 | Inventory | Inventory Statistics Dashboard | Summary stats for inventory | Total items, total value, low stock count, expiring count | Completed | 2026-03-30 | 7373b4e | P1 |  | Pending |  | Analytics | API: /api/inventory/stats
F029 | Inventory | Inventory Lookup/Search API | Quick search for inventory items | Search by name, SKU, barcode for use in billing/PO forms | Completed | 2026-03-30 | f572d67 | P1 |  | Pending |  |  | API: /api/inventory/lookup
F030 | Inventory | Bulk Stock Operations | Bulk update stock quantities | Bulk stock adjustment API for multiple items at once | Completed | 2026-03-30 | 7373b4e | P1 |  | Pending |  |  | API: /api/inventory/bulk
F031 | Inventory | CSV/Excel Bulk Import | Import inventory from CSV/Excel files | Upload page with drag-drop, column mapping, validation, error reporting, batch create | Completed | 2026-03-30 | 7373b4e | P1 |  | Pending |  | Bulk Operations | API: /api/inventory/import
F032 | Inventory | Stock Audit Page | Physical stock count reconciliation | Full audit page with barcode scanning, manual entry, discrepancy detection | Completed | 2026-03-30 | 4331cc9 | P0 |  | Pending |  | Audit Trail | Barcode scanner integration
F033 | Inventory | Stock Audit API | Backend for stock audit operations | Submit audit counts, calculate discrepancies, record adjustments | Completed | 2026-03-30 | 7373b4e | P0 |  | Pending |  |  | API: /api/inventory/stock-audit
F034 | Inventory | Barcode/QR Scanning Component | Scan barcodes for stock operations | Reusable BarcodeScanner component, used in audit, receiving, and lookup | Completed | 2026-03-30 | 4331cc9 | P1 |  | Pending |  | Smart Scanning | src/components/BarcodeScanner.tsx
F035 | Inventory | Supplier Management Page | Manage supplier directory | Supplier list page with CRUD, linked to POs and inventory items | Completed | 2026-03-30 | f572d67 | P0 |  | Pending
F036 | Inventory | Supplier CRUD API | Create/edit/delete suppliers | Full REST API for supplier management with contact details | Completed | 2026-03-30 | f572d67 | P0 |  | Pending |  |  | API: /api/suppliers, /api/suppliers/[id]
F037 | Inventory | Purchase Orders List Page | View all purchase orders | Filterable list with status (draft/submitted/partial/received/cancelled) | Completed | 2026-03-30 | 8095ccd | P0 |  | Pending |  | Procurement
F038 | Inventory | Create Purchase Order Page | Form to create new PO | Select supplier, add line items, quantities, prices, branch selection | Completed | 2026-03-30 | 8095ccd | P0 |  | Pending |  |  | Branch-aware since 7b18ad9
F039 | Inventory | Purchase Order Detail Page | View/manage single PO | Full PO view with status actions, line items, receive button | Completed | 2026-03-30 | 8095ccd | P0 |  | Pending
F040a | Inventory | PO Status Workflow | Draft → Submitted → Partial → Received | Status change API with validation rules | Completed | 2026-03-30 | 8095ccd | P0 |  | Pending |  |  | API: /api/purchase-orders/[id]/status
F040b | Inventory | PO Receiving Workflow | Receive goods against POs | Partial receiving, quantity validation, auto-stock-update on receive | Completed | 2026-03-30 | 8095ccd | P0 |  | Pending |  |  | API: /api/purchase-orders/[id]/receive
F040c | Inventory | Smart PO Suggestions | Auto-suggest items needing reorder | Algorithm based on current stock vs reorder point, consumption rate, fast-moving items | Completed | 2026-03-30 | 8095ccd | P1 |  | Pending |  | AI-Powered | API: /api/purchase-orders/suggestions
F040d | Inventory | Branch-Aware Purchase Orders | POs linked to specific branch | Branch selector on PO, received stock goes to correct branch | Completed | 2026-03-30 | 7b18ad9 | P0 |  | Pending |  | Multi-Branch
F041a | Inventory | Stock Transfers List Page | View all inter-branch transfers | Filterable list by status, source/destination branch, date | Completed | 2026-03-30 | dadee2c | P0 |  | Pending |  | Multi-Branch
F041b | Inventory | Create Transfer Page | Form to initiate stock transfer | Select source/dest branch, add items with quantities, notes | Completed | 2026-03-30 | dadee2c | P0 |  | Pending
F041c | Inventory | Transfer Detail Page | View/manage single transfer | Full view with items, status actions (submit/receive/cancel) | Completed | 2026-03-30 | dadee2c | P0 |  | Pending |  |  | Fixed: 615e22f, e2ba711
F041d | Inventory | Transfer Submit/Receive/Cancel APIs | Complete transfer lifecycle | Submit (deduct source stock), Receive (add dest stock), Cancel (reverse) | Completed | 2026-03-30 | dadee2c | P0 |  | Pending |  |  | 4 API routes for transfer actions
F041e | Inventory | Transfer Templates | Save and reuse frequent transfers | Template CRUD, apply template to pre-fill new transfer items | Completed | 2026-03-31 | 91d2fb3 | P2 |  | Pending |  | Efficiency | API: /api/transfers/templates
F041f | Inventory | Transfer Notifications | Notify branches of incoming transfers | Notification model with bell icon in header, unread count badge | Completed | 2026-03-30 | 7e37183 | P1 |  | Pending |  |  | API: /api/notifications
F042a | Inventory | Branch Stock Page | View stock levels per branch | Branch-specific stock listing with totals and summary cards | Completed | 2026-03-30 | c853141 | P0 |  | Pending |  | Multi-Branch
F042b | Inventory | Multi-Branch Stock Comparison | Side-by-side stock comparison across branches | Comparison view with filtering, highlights low stock per branch | Completed | 2026-03-30 | 95a6f8d | P1 |  | Pending |  | Multi-Branch | API: /api/inventory/branch-comparison
F042c | Inventory | Branch Stock API | Backend for branch-level stock queries | Stock levels, branch totals, per-item per-branch breakdown | Completed | 2026-03-30 | c853141 | P0 |  | Pending |  |  | API: /api/branches/stock
F043a | Inventory | Alerts Dashboard Page | Central alert management | Combined view of low stock alerts + expiry alerts with action buttons | Completed | 2026-03-30 | 4ba2d4a | P0 |  | Pending |  | Compliance
F043b | Inventory | Low Stock Alerts | Alert when stock falls below reorder point | Alert API + badge counts + doctor portal card showing low stock items | Completed | 2026-03-30 | 616ffff | P0 |  | Pending |  |  | API: /api/inventory/alerts
F043c | Inventory | Expiry Management & Auto-Alerts | Track and alert on expiring items | Auto-check for items expiring within 30/60/90 days, write-off workflow | Completed | 2026-03-30 | 4ba2d4a | P0 |  | Pending |  | Compliance | API: /api/inventory/expiry-check
F043d | Inventory | Expired Stock Write-Off | Write off expired stock per branch | Branch-level write-off with reason, auto-deduct stock, transaction record | Completed | 2026-03-30 | 4ba2d4a | P1 |  | Pending |  |  | API: /api/inventory/write-off-expired
F044a | Inventory | Stock Movement History Graph | Visualize stock movement trends | Interactive chart on item detail page showing stock over time | Completed | 2026-03-30 | dff7926 | P2 |  | Pending |  | Analytics
F044b | Inventory | Inventory Reports Page | Comprehensive stock analytics | Valuation report, movement report, expiry report, low-stock report with date filters | Completed | 2026-03-30 | 7373b4e | P1 |  | Pending |  | Analytics | API: /api/reports/inventory
F044c | Inventory | Transfer Reports | Report on inter-branch transfer activity | Transfer volume, branch activity, date range and branch filters | Completed | 2026-03-30 | 004b1e2 | P2 |  | Pending |  |  | API: /api/reports/transfers
F044d | Inventory | Indent/Requisition API | Internal stock request between departments | Indent request creation and approval workflow | Completed | 2026-03-30 | 7373b4e | P2 |  | Pending |  |  | API: /api/inventory/indent
F045a | Inventory | InventoryTabs Navigation Component | Consistent tab navigation across all inventory pages | Reusable InventoryTabs component with active state highlighting | Completed | 2026-03-31 | a9fafd6 | P1 |  | Pending |  |  | Fixed duplicate tabs bug
F045b | Inventory | Header Consistency Fix | Consistent headers across inventory sub-pages | Unified page headers, back buttons, padding, grid layout | Completed | 2026-03-31 | 2b69c86 | P1 |  | Pending
F045c | Inventory | Branch-Stock Card Colors Fix | Summary cards using correct YODA design tokens | Fixed hardcoded colors to use CSS variables from design system | Completed | 2026-03-31 | e08d700 | P1 |  | Pending
F045d | Inventory | Navigation Consistency Fix | Tabs, back buttons, padding across all pages | Unified navigation patterns, consistent spacing | Completed | 2026-03-31 | e307402 | P1 |  | Pending
F045e | Inventory | A-Z Sorting Fix | Inventory sorted alphabetically by default | Fixed sorting across all inventory list endpoints | Completed | 2026-03-30 | ef27e26 | P1 |  | Pending
F045f | Inventory | Inventory Seed Data | Pre-populated inventory for Railway | 80+ Ayurvedic products seeded with variants, prices, stock levels | Completed | 2026-03-30 | c130bdc | P0 |  | Pending
F045g | Inventory | End-to-End Bug Fixes | 6 bugs found in code audit | Fixed transfer receive mapping, detail page data, and other issues | Completed | 2026-03-30 | acfd45e | P0 |  | Pending |  |  | Commits: e2ba711, 615e22f, acfd45e
F046a | Inventory | Branch-Aware Dashboard | Dashboard shows branch-specific data | Dashboard stats filtered by selected branch | Completed | 2026-03-30 | c853141 | P0 |  | Pending |  | Multi-Branch
F046b | Inventory | Branch-Aware Billing | Billing filtered by branch | Branch dropdown filter on billing list page | Completed | 2026-03-30 | 685785a | P1 |  | Pending |  | Multi-Branch
F046c | Inventory | Branch-Aware Reports | Reports filtered by branch | Branch filter on revenue, inventory, and transfer reports | Completed | 2026-03-30 | c853141 | P1 |  | Pending |  | Multi-Branch
F046d | Inventory | Branch-Aware Stock Audit | Audit stock per branch | Branch selection in stock audit page | Completed | 2026-03-30 | c853141 | P0 |  | Pending |  | Multi-Branch
F046e | Inventory | Low Stock Alert in Doctor Portal | Doctors see low stock for their branch | Low stock card on doctor dashboard showing critical items | Completed | 2026-03-30 | 616ffff | P1 |  | Pending
F040 | Billing | Invoice Generation | Create invoices for services | Auto-generate invoices with line items, tax, discounts | Completed | 2026-03-28 | 3fd92f7 | P0 |  | Pending
F041 | Billing | Payment Recording | Record payments against invoices | Multiple payment methods, partial payments, payment history | Completed | 2026-03-28 | 3fd92f7 | P0 |  | Pending
F042 | Billing | Credit Notes | Issue refunds/credits | Credit note creation, link to invoice | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F043 | Billing | Branch Filter | Filter billing by branch | Branch dropdown filter on billing list page | Completed | 2026-03-30 | 685785a | P1 |  | Pending |  | Multi-Branch
F044 | Billing | Billing Statistics | Dashboard stats for billing | Revenue stats API with period filters | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F050 | Doctor Portal | Doctor Dashboard | Dedicated doctor view | Today's appointments, patients, low stock alerts | Completed | 2026-03-29 | 11d63fa | P0 |  | Pending |  | Role-Based Access
F051 | Doctor Portal | Prescriptions | Write and manage prescriptions | Prescription CRUD with items, dosage, duration | Completed | 2026-03-29 | 11d63fa | P0 |  | Pending
F052 | Doctor Portal | Clinical Notes | Add clinical notes to patient visits | Rich text notes with attachments | Completed | 2026-03-28 | 3fd92f7 | P0 |  | Pending
F060 | Admin | Authentication System | Secure login | JWT-based auth with role-based access (admin/doctor/staff) | Completed | 2026-03-28 | 3fd92f7 | P0 |  | Pending |  | Security
F061 | Admin | Two-Factor Authentication (2FA) | TOTP-based 2FA | Setup, verify, disable TOTP with QR code generation | Completed | 2026-03-28 | 3fd92f7 | P0 |  | Pending |  | Security
F062 | Admin | Staff Management | Manage clinic staff | Unified User model with roles, invite system, password management | Completed | 2026-03-28 | b38c37c | P0 |  | Pending
F063 | Admin | Audit Log | Track all system changes | AuditLog model with user, action, timestamp, details | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending |  | Compliance
F064 | Admin | Branch Management | Multi-branch support | Branch CRUD, branch-level stock, branch-aware operations | Completed | 2026-03-30 | c853141 | P0 |  | Pending |  | Multi-Branch
F065 | Admin | Branding — Ayur Centre | Rebrand from PatientReg | Logo, app name, sidebar, all pages updated | Completed | 2026-03-28 | 1fa296b | P0 |  | Pending
F070 | Communications | Email Integration | Send emails to patients | Email sending with template support | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F071 | Communications | WhatsApp Integration | Send WhatsApp messages | WhatsApp API integration | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F072 | Communications | Message Templates | Reusable message templates | Template CRUD with variable substitution, preview | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F073 | Communications | Bulk Messaging | Send messages to multiple patients | Bulk send with filtering, progress tracking | Completed | 2026-03-28 | 3fd92f7 | P2 |  | Pending
F074 | Communications | Appointment Reminders | Auto-send reminders | Auto-schedule, manual send, bulk reminders | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending |  | Automation
F080 | Packages | Package Management | Create treatment packages | Packages with sessions, pricing, validity | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F081 | Packages | Session Tracking | Track package session usage | Session booking, completion, remaining count | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending
F082 | Packages | Package Sharing | Share packages between family members | Share API with linked patients | Completed | 2026-03-28 | 3fd92f7 | P2 |  | Pending
F083 | Packages | Package Refunds | Process package refunds | Pro-rated refund calculation | Completed | 2026-03-28 | 3fd92f7 | P2 |  | Pending
F085 | Treatment Plans | Treatment Plan Builder | Create structured treatment plans | Multi-item plans with milestones and progress tracking | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending |  | Clinical Excellence
F090 | Reports | Revenue Reports | Revenue analytics | Date range, branch filter, summary stats | Completed | 2026-03-28 | 3fd92f7 | P1 |  | Pending |  | Analytics
F091 | Reports | Inventory Reports | Stock analytics | Valuation, movement, expiry, low-stock reports | Completed | 2026-03-30 | 7373b4e | P1 |  | Pending
F092 | Reports | Insurance Reports | Insurance claim analytics | Claim status, provider breakdown | Completed | 2026-03-28 | 3fd92f7 | P2 |  | Pending
F093 | Reports | Transfer Reports | Stock transfer analytics | Transfer volume, branch activity | Completed | 2026-03-30 | 004b1e2 | P2 |  | Pending
F100 | DevOps | Railway Deployment | Deploy to Railway with persistent storage | SQLite on persistent volume, auto-seed on deploy | Completed | 2026-03-29 | 001c9f9 | P0 |  | Pending |  | Cloud Hosted
F101 | DevOps | Data Seeding | Pre-populate with test data | Doctors, therapists, patients, inventory all seeded | Completed | 2026-03-30 | 2c500ae | P0 |  | Pending
F110 | Patients | Multi-Country ID Selector | Dropdown for ID type (NRIC/Aadhaar/Passport) | Analysis completed, code pending | Planned |  |  | P1 |  |  |  | Multi-Country | Part of localization roadmap
F111 | Patients | Address Structure per Country | SG: Block/Street/Unit/Postal ¦ IN: different format | Analysis completed, code pending | Planned |  |  | P1 |  |  |  | Multi-Country
F112 | Patients | Database Unique Constraints | Add partial unique indexes for NRIC, phone, email | Analysis completed, code pending | Planned |  |  | P1 |  |  |  | Data Integrity | Step 4 of duplicate prevention
F113 | Patients | Duplicate Merge Tool | Admin tool to merge duplicate patient records | Analysis completed, code pending | Planned |  |  | P2 |  |  |  |  | Step 5 of duplicate prevention

## Validation Checklist
Field | Module | Validation Rule | Frontend? | API? | Country | Status | Tested By | Test Date | Notes
First Name | Patients | Required, trimmed, non-empty | Yes | Yes | All | Done |  |  | Unicode, hyphens, apostrophes accepted
Last Name | Patients | Required, trimmed, non-empty | Yes | Yes | All | Done |  |  | Should become optional for India (mononyms)
NRIC ID | Patients | 9 chars: S/T/F/G/M + 7 digits + checksum letter | Yes | Yes | SG | Done |  |  | Auto-uppercase, checksum algorithm validated
NRIC Duplicate | Patients | Hard block — cannot save if NRIC already exists | Yes | Yes | SG | Done |  |  | Shows existing patient link
Phone (Primary) | Patients | Required, SG 8-digit / IN 10-digit / International +XX | Yes | Yes | SG/IN | Done |  |  | Normalized to +65/+91 on save
Phone Duplicate | Patients | Soft warning — can override with 'Different person' | Yes | Yes | All | Done |  |  | Suffix matching for country code differences
Phone Normalization | Patients | Strip formatting, add +65 (SG) or +91 (IN) prefix | No | Yes | SG/IN | Done |  |  | Applied to all phone fields on save
Secondary Mobile | Patients | Optional, valid phone format, ≠ primary mobile | Yes | Yes | All | Done |  |  | Cross-field validation
Emergency Phone | Patients | Optional, valid phone, ≠ patient's own number | Yes | Yes | All | Done |  |  | Cross-field validation
Email | Patients | Optional, valid format, case-insensitive duplicate check | Yes | Yes | All | Done |  |  | Lowercased on save
Email Duplicate | Patients | Soft warning — can override | Yes | No | All | Done
Gender | Patients | Required, must be male/female/other | Yes | Yes | All | Done |  |  | Radio buttons
Date of Birth | Patients | Optional, valid date or age entry | Yes | No | All | Done |  |  | DOB or age toggle
Aadhaar (India) | Patients | 12 digits with Verhoeff checksum | No | No | IN | Planned |  |  | Part of multi-country ID support
Passport | Patients | Alphanumeric, country-specific format | No | No | All | Planned |  |  | Part of multi-country ID support

## Git History
Commit | Date | Description | Module | Type
7ca6dcd | 2026-03-31 | Add NRIC checksum validation, phone normalization, and cross-field checks | Patients | Feature
3a627ea | 2026-03-31 | Redesign patient form: label-input layout, 350px field width, duplicate detection | Patients | Feature
0ffb9b3 | 2026-03-31 | Reorder patient registration form to match patient detail view | Patients | Enhancement
4387814 | 2026-03-31 | Fix patient form layout: compact fields, consistent spacing | Patients | Fix
2a30cc8 | 2026-03-31 | Redesign patient registration form: layout, dropdowns, SG address | Patients | Feature
e08d700 | 2026-03-31 | Fix branch-stock summary card colors to use YODA tokens | Inventory | Fix
a9fafd6 | 2026-03-31 | Fix duplicate InventoryTabs on branch-stock page | Inventory | Fix
2b69c86 | 2026-03-31 | Fix header consistency across all inventory sub-pages | Inventory | Fix
e307402 | 2026-03-31 | Fix navigation consistency: tabs, back buttons, padding, grid | UI/UX | Fix
91d2fb3 | 2026-03-31 | Add transfer templates: save and reuse frequent transfers | Inventory | Feature
95a6f8d | 2026-03-30 | Add multi-branch stock comparison view | Inventory | Feature
dff7926 | 2026-03-30 | Add stock movement history graph to inventory item detail | Inventory | Feature
685785a | 2026-03-30 | Add branch filter to billing list | Billing | Feature
4ba2d4a | 2026-03-30 | Add expiry management: auto-alerts, branch write-off, enhanced alerts | Inventory | Feature
acfd45e | 2026-03-30 | Fix 6 bugs from end-to-end code audit | Multiple | Fix
e2ba711 | 2026-03-30 | Fix transfer receive: map transfer item ID to inventory item ID | Inventory | Fix
615e22f | 2026-03-30 | Fix transfer detail page: map nested item data to flat structure | Inventory | Fix
4331cc9 | 2026-03-30 | Add barcode/QR scanning for stock audit and receiving | Inventory | Feature
7e37183 | 2026-03-30 | Add notification system for transfer alerts | Inventory | Feature
004b1e2 | 2026-03-30 | Add transfer reports to inventory and main reports pages | Reports | Feature
616ffff | 2026-03-30 | Add low stock alert card to doctor portal dashboard | Doctor Portal | Feature
7b18ad9 | 2026-03-30 | Add branch awareness to Purchase Orders | Inventory | Feature
ef27e26 | 2026-03-30 | Fix inventory sorting to A-Z by name across all endpoints | Inventory | Fix
c853141 | 2026-03-30 | Add branch awareness across billing, reports, dashboard, and stock audit | Multi-Branch | Feature
dadee2c | 2026-03-30 | Add stock transfers between branches feature | Inventory | Feature
2c84221 | 2026-03-30 | Add sub-tabs and enriched transaction history on inventory detail page | Inventory | Enhancement
8095ccd | 2026-03-30 | Add smart PO suggestions, receiving workflow, and fast-moving items | Inventory | Feature
7373b4e | 2026-03-30 | Add P1+P2 inventory features: import, stock audit, reports, indent | Inventory | Feature
2c500ae | 2026-03-30 | Seed all data to Railway: patients, appointments, invoices, treatments | DevOps | Enhancement
c130bdc | 2026-03-30 | Add inventory seed for Railway + fix build error | DevOps | Fix
f572d67 | 2026-03-30 | Inventory overhaul: correct units, variant support, billing variant picker | Inventory | Feature
1baa2e2 | 2026-03-29 | Move db push and seed to start script for Railway volume | DevOps | Fix
d9d858c | 2026-03-29 | Trigger redeploy for Railway volume support | DevOps | Fix
1d94f95 | 2026-03-29 | Fix build errors preventing Railway deployment | DevOps | Fix
16eb698 | 2026-03-29 | Fix DB path: simplify to always use dev.db unless DB_PATH is set | DevOps | Fix
bbf8671 | 2026-03-29 | Seed all doctors, therapists, and patients on every deploy | DevOps | Enhancement
001c9f9 | 2026-03-29 | Fix data loss on Railway: use persistent volume for SQLite database | DevOps | Fix
5933f75 | 2026-03-29 | Add Set Password button in Admin Staff page for managing doctor logins | Admin | Feature
11d63fa | 2026-03-29 | Add doctor portal, prescriptions, PDF export, role-based access, and staff password management | Doctor Portal | Feature
b38c37c | 2026-03-28 | Unify staff management: merge Doctor model into User with role-based access | Admin | Feature
1fa296b | 2026-03-28 | Rebrand app from PatientReg to Ayur Centre Pte. Ltd. | Admin | Enhancement
7dee12a | 2026-03-28 | Add admin seed to build script for Railway deployment | DevOps | Enhancement
3fd92f7 | 2026-03-28 | Clinic management system with auth, 2FA, and full features | All | Feature
6bc9deb | 2026-03-25 | Initial commit from Create Next App | DevOps | Init

## Marketing Copy
Category | Feature Headline | One-Liner Description | Key Benefit | Target Audience | Screenshot Needed?
Patient Management | Smart Patient Registration | 30+ field registration with NRIC validation, duplicate detection, and auto-normalization | Zero duplicate records, Singapore-compliant | Clinic Admin | Yes
Patient Management | Real-Time Duplicate Prevention | Instant alerts when NRIC, phone, or email matches an existing patient | Prevents data entry errors before they happen | Clinic Admin | Yes
Patient Management | Singapore NRIC Checksum Validation | Built-in NRIC/FIN checksum verification catches typos instantly | Singapore regulatory compliance | Clinic Owner | Yes
Inventory | End-to-End Inventory Management | From purchase orders to stock audit, with barcode scanning and expiry tracking | Complete visibility into stock at every branch | Operations Manager | Yes
Inventory | Multi-Branch Stock Transfers | Transfer stock between branches with templates, notifications, and full tracking | Optimized stock distribution across locations | Operations Manager | Yes
Inventory | Smart Reorder Suggestions | AI-powered purchase order suggestions based on consumption patterns | Never run out of critical supplies | Procurement | Yes
Inventory | Barcode & QR Scanning | Scan products during stock audit and receiving for error-free operations | Faster, more accurate stock counts | Warehouse Staff | Yes
Inventory | Expiry Alert Dashboard | Automated tracking and branch-level write-off for expiring products | Reduce waste, ensure patient safety | Quality Manager | Yes
Doctor Portal | Dedicated Doctor Dashboard | Personalized view with today's patients, prescriptions, and alerts | Doctors see only what matters to them | Doctors | Yes
Billing | Comprehensive Billing Suite | Invoicing, payments, credit notes, and insurance claims in one place | Streamlined revenue collection | Billing Staff | Yes
Security | Enterprise-Grade Security | JWT authentication, TOTP 2FA, role-based access, and complete audit trail | PDPA-compliant data protection | Clinic Owner | Yes
Multi-Branch | Multi-Branch Operations | Manage inventory, billing, and staff across all your clinic locations | Scale your practice without scaling complexity | Clinic Owner | Yes
Communications | Patient Communication Hub | Email, WhatsApp, SMS with templates, bulk messaging, and auto-reminders | Reduce no-shows and improve engagement | Clinic Admin | Yes
Packages | Treatment Package Management | Sell packages, track sessions, share between family members, process refunds | Increase revenue through package offerings | Clinic Owner | Yes
Analytics | Business Intelligence Reports | Revenue, inventory, insurance, and transfer analytics with branch breakdowns | Data-driven decisions for growth | Clinic Owner | Yes

## Testing Tracker
Test ID | Module | Test Scenario | Steps to Test | Expected Result | Tester | Status | Date Tested | Bug ID | Notes
T001 | Patients | NRIC valid checksum accepted | Enter S1234567D in NRIC field, tab out | No error shown, green border |  | Pending
T002 | Patients | NRIC invalid checksum rejected | Enter S1234567A in NRIC field, tab out | Red border + 'Invalid NRIC checksum' error |  | Pending
T003 | Patients | NRIC auto-uppercase | Type s1234567d in NRIC field | Auto-converts to S1234567D |  | Pending
T004 | Patients | NRIC wrong prefix rejected | Enter X1234567A, tab out | Error: 'NRIC must start with S, T, F, G, or M' |  | Pending
T005 | Patients | NRIC duplicate hard block | Enter existing NRIC, try to save | Red warning with link to existing patient, save blocked |  | Pending
T006 | Patients | Phone duplicate soft warning | Enter existing phone number | Yellow warning with 'Different person, continue' option |  | Pending
T007 | Patients | Phone normalization (SG) | Enter 91234567 as phone, save patient | Stored as +6591234567 in database |  | Pending |  |  | Check patient detail page
T008 | Patients | Phone normalization (IN) | Enter 9876543210 as phone, save patient | Stored as +919876543210 in database |  | Pending
T009 | Patients | Secondary ≠ Primary phone | Enter same number in Mobile and Secondary Mobile, save | Error: 'Secondary mobile cannot be the same as primary' |  | Pending
T010 | Patients | Emergency ≠ Own phone | Enter same number in Mobile and Emergency Phone, save | Error: 'Emergency contact should be different from patient's own number' |  | Pending
T011 | Patients | Email duplicate soft warning | Enter existing email | Yellow warning with override option |  | Pending
T012 | Patients | Required fields validation | Leave First Name, Last Name, Gender, Phone empty and save | All 4 fields show error messages |  | Pending
T013 | Inventory | Inventory list loads with A-Z sorting | Go to Inventory page | Items listed alphabetically, search works, categories filter |  | Pending
T014 | Inventory | Create new inventory item | Inventory > New > Fill form > Save | Item created with name, category, unit, reorder point, supplier |  | Pending
T015 | Inventory | Add variant to item | Edit item > Add variant (e.g., 100ml, 200ml) | Variants appear in item detail and billing picker |  | Pending
T016 | Inventory | Item detail — sub-tabs work | Click item > Check Overview, Transactions, Movement Graph tabs | All tabs load correct data, graph shows stock history |  | Pending
T017a | Inventory | CSV bulk import | Inventory > Import > Upload CSV | Items imported, validation errors shown, duplicates caught |  | Pending
T018 | Inventory | Stock audit with barcode scan | Stock Audit > Scan barcode > Enter count | Item found by barcode, discrepancy calculated vs system stock |  | Pending
T019 | Inventory | Create purchase order | PO > New > Select supplier, add items, save | PO created in Draft status, items and quantities correct |  | Pending
T020a | Inventory | PO status workflow | Submit PO > Receive partial > Receive remaining | Status: Draft → Submitted → Partial → Received, stock updated |  | Pending
T021 | Inventory | Smart PO suggestions | PO > Check suggestions | Items below reorder point suggested with recommended quantities |  | Pending
T022 | Inventory | Create stock transfer | Transfers > New > Select branches, add items, submit | Stock deducted from source branch immediately |  | Pending
T023 | Inventory | Receive stock transfer | Open pending transfer at dest branch > Receive | Stock added to destination, transfer marked Received |  | Pending
T024 | Inventory | Cancel stock transfer | Open submitted transfer > Cancel | Stock restored to source branch, transfer marked Cancelled |  | Pending
T025 | Inventory | Transfer template save & apply | Create transfer > Save as template > New transfer > Apply template | Template pre-fills items, quantities, branches |  | Pending
T026 | Inventory | Transfer notification | Submit transfer to another branch | Bell icon shows unread notification at destination branch |  | Pending
T027 | Inventory | Multi-branch stock comparison | Branch Stock > Comparison view | Side-by-side stock levels for all branches, low stock highlighted |  | Pending
T028 | Inventory | Expiry alert triggers | Add item with expiry < 30 days | Appears in Alerts dashboard under expiry section |  | Pending
T029 | Inventory | Low stock alert | Reduce stock below reorder point | Appears in Alerts + Doctor Portal dashboard card |  | Pending
T030 | Inventory | Write off expired stock | Alerts > Expiry > Write Off | Stock quantity reduced, write-off transaction recorded |  | Pending
T031 | Inventory | Supplier CRUD | Suppliers page > Add/Edit/Delete supplier | Supplier saved, appears in PO supplier dropdown |  | Pending
T032 | Inventory | Inventory reports page | Reports > Inventory | Valuation, movement, expiry, low-stock reports with date filters |  | Pending
T033 | Inventory | Transfer reports | Reports > Transfers | Transfer volume, branch activity with date/branch filters |  | Pending
T034 | Inventory | Branch-aware PO | Create PO with branch selection | Received stock goes to selected branch only |  | Pending
T035 | Inventory | InventoryTabs navigation | Click through all inventory sub-pages | Tabs highlight correctly, no duplicate tabs, consistent headers |  | Pending
T040 | Billing | Create and pay invoice | Billing > New > Add items > Save > Record payment | Invoice marked as paid, payment recorded |  | Pending
T041 | Billing | Branch filter on billing | Billing page > Select branch from dropdown | Only invoices for selected branch shown |  | Pending
T042 | Billing | Credit note creation | Open paid invoice > Issue credit note | Credit note created, linked to original invoice |  | Pending
T043 | Admin | Login with 2FA | Login with credentials, enter TOTP code | Successful login, redirected to dashboard |  | Pending
T044 | Admin | Role-based access | Login as doctor, try to access admin page | Access denied / redirected to doctor portal |  | Pending
T045 | Admin | Branch management | Admin > Branches > Create new branch | Branch appears in all branch dropdowns |  | Pending
T046 | Admin | Staff invite flow | Admin > Staff > Invite new user | Invite email sent, user can set password via link |  | Pending
T047 | Admin | Audit log records actions | Perform any CRUD action, check Admin > Audit Log | Action logged with user, timestamp, details |  | Pending
T048 | Doctor Portal | Doctor dashboard loads | Login as doctor, check dashboard | Today's appointments, low stock alerts, quick actions shown |  | Pending
T049 | Doctor Portal | Write prescription | Open patient > Prescriptions > New | Prescription created with items, dosage, duration |  | Pending
T050 | Communications | Send WhatsApp message | Patient detail > Communications > Send WhatsApp | Message sent via WhatsApp API |  | Pending
T051 | Packages | Purchase and use package | Packages > Buy for patient > Book session | Session counted, remaining sessions decremented |  | Pending